## WBS Working Doc
0 | Piloted Data Analysis |  |  | EF+1 | ES+D-1 | LF-D+1
|  | Predecessor | Duration (days) | Start | End | LS | LF | Resource
0.11 | Identification of business problem
0.11.1 | Review of mission statements |  | 2 | 1 | 2 | 38 | 39 | In-house stakeholders: CEO, Sponsor, Mission Statement. Documents, Analyst
0.11.2 | Research on problem statement | 0.11.1 | 3 | 1 | 3 | 37 | 39 | Analyst
0.12 | Requirements Understanding
0.12.1 | Engage Stakeholders |  | 14 | 4 | 17 | 23 | 36 | In-house staff: CEO, Sponsor, Data Steward, IT specialist, Analyst
0.12.2 | Inclusion of right variables | 0.11.2 | 1 | 4 | 4 | 36 | 36 | Data frame variables, Analyst
0.12.3 | Distinction between variables | 0.11.2 | 1 | 4 | 4 | 36 | 36 | Variables, Analyst
0.12.4 | Resolution of analysis type | 0.11 | 1 | 4 | 4 | 36 | 36 | Analysis types: Regression, Classification, xxx, xxxx, Analyst
0.13 | Selection of Analysis Platform
0.13.1 | Examination of volumn of data |  | 1 | 18 | 18 | 22 | 22 | Dataset, Infrasture Staff, Analyst
0.13.2 | Requirement of Processing Speed |  | 1 | 18 | 18 | 22 | 22 | Analyst
0.14 | Dataset Collection
0.14.1 | Identification of data source | 0.12.1 | 3 | 19 | 21 | 19 | 21 | Internal documents, Files, Conversations, etc External: Internet, Social media, xxx, In-house staff, Analyst
0.14.2 | Selection of personnel | 0.12.1 | 2 | 19 | 20 | 20 | 21 | In-house staff, Analyst
0.15 | Required Libraries
0.15.1 | Selection of needed libraries | 0.11 | 1 | 22 | 22 | 0 | 18 | Built-in libraries (Python R), Analyst
0.16 | Dataset Visualization
0.16.1 | Choice of visualization tool | 0.11 | 1 | 23 | 23 | 0 | 0 | Data tools(Python, R, Jupyter Notebook, KNIME, AWS), Analyst
0.16.2 | Selection of visualization features | 0.11. 0.12.2, 0.12.3, 0.12.4 | 1 | 23 | 23 | 0 | 0 | Dataset, Visualization tool, Analyst
0.17 | Data Integrity checks | Predecessor
0.17.1 | Review Distribution Shape | 0.16.1 | 1 | 24 | 24 | 0 | 0 | Dataset, Library packages, Analyst
0.17.2 | Check for Missing Values | 0.16.1 | 1 | 24 | 24 | 0 | 0 | Dataset, Library packages, Analyst
0.17.3 | Check for data imbalance | 0.16.1 | 1 | 24 | 24 | 0 | 0 | Dataset, Library packages, Analyst
0.17.4 | Check for Outliers | 0.16.1 | 1 | 24 | 24 | 0 | 0 | Dataset, Library packages, Analyst
0.17.5 | Examine category labels | 0.16.1 | 1 | 24 | 24 | 0 | 0 | Dataset, Library packages, Analyst
0.17.6 | Check for scale of magnitude | 0.16.2 | 1 | 24 | 24 | 0 | 0 | Dataset, Library packages, Analyst
0.17.7 | Variable ineffectiveness | 0.16.3 | 1 | 24 | 24 | 0 | 0 | Dataset, Library packages, Analyst
0.17.8 | Variable correlation | 0.16.4 | 1 | 24 | 24 | 0 | 0 | Dataset, Library packages, Analyst
0.18 | Right Fit Model Selection
0.18.1 | Examine business question | 0.11.1, 0.11.2, 0.14.2 | 1 | 25 | 26 | 0 | 0 | CEO, Data Stewards, Business questions, Analyst
0.18.2 | Understand algorithm differences |  | 1 | 25 | 26 | 0 | 0 | Algorithms, Analyst
0.18.3 | Selection of right model | 0.18.1, 0.18.2 | 1 | 25 | 26 | 0 | 0 | Model types, Business problem, Analyst
0.19 | Training Model
0.19.1 | Selection of training data | 0.17.1 | 1 | 27 | 27 | 0 | 0 | Library packages, Model functions, Dataset, Analyst
0.19.2 | Selection of model parameters | 0.18.1, 0.18.3 | 1 | 27 | 27 | 0 | 0 | Library packages, Model functions, Dataset, Parameters, Analyst
0.19.3 | Training run |  | 3 | 27 | 29 | -2 | 0
0.2 | Testing Model
0.20.1 | Selection of test size | 0.17.1 | 1 | 30 | 30 | 0 | 0 | Library packages, Model functions, Dataset, Analyst
0.20.2 | Selection of model parameters | 0.18.1, 0.18.3 | 1 | 30 | 30 | 0 | 0 | Library packages, Model functions, Dataset, Parameters, Analyst
0.21 | Evaluated Model Selection
0.21.1 | Understand KPI differences |  | 1 | 31 | 31 | 0 | 0 | KPI types (CM, F score, Recall, Precission, Accuracy), Analyst
0.21.2 | Selection of right KPI | 0.20.1 | 1 | 31 | 31 | 0 | 0 | KPI types, Analyst
0.21.3 | Assessment of model | 0.21.1, 0.21.2 | 1 | 31 | 31 | 0 | 0 | KPI types, Analyst
0.22 | Refined Model
0.22.1 | Comparision of model runs | 0.20.1, 0.21.2, 0.21.3 | 1 | 32 | 33 | 0 | 0 | Analyst
0.22.2 | Selection of model | 0.21.1, 0.21.2, 0.21.3, 0.22.1 | 1 | 32 | 33 | 0 | 0 | Analyst
0.23 | Deployed Model
0.23.1 | Selection of platform |  | 4 | 34 | 37 | -3 | 0 | Infrasture Staff, Analyst
0.23.2 | Selective Parameters for Deployment | 0.23.1 | 1 | 34 | 34 | 0 | 0 | Analyst
0.24 | Results Reporting
0.24.1 | Selection of Audience | 0.12.1 | 1 | 38 | 38 | -3 | -3 | In-house staff: CEO, Data Steward, Analyst
0.24.2 | Selection of presentation format | 0.24.1 | 1 | 38 | 38 | 0 |  | Formats (PP, Graphs), Anayst
0.25 | Model Monitor & Review
0.25.1 | Change model size | 0.19.1, 0.19.2, 0.20.1, 0.20.2 | 1 | 39 | 39 | -3 | -3 | Input values, Dataset, Analyst
0.25.2 | Change input parameters | 0.19.2, 0.20.2 | 1 | 39 | 39 | -3 | -3 | Input values, Dataset, Analyst

## WBS
0 | Piloted Data Analysis
0.11 | Identification of business problem
0.11.1 | Review of mission/vision statements
0.11.2 | Research findings on problems
0.12 | Requirements Understanding
0.12.1 | Engage Stakeholders
0.12.2 | Inclusion of right variables for analysis
0.12.3 | Clarification between variables: predictor and predicted
0.12.4 | Expectation of analysis results: numerical, classification. prediction
0.13 | Selection of Analysis Platform
0.13.1 | Examination of volumn of data
0.13.2 | Requirement of Processing Speed
0.14 | Dataset Collection
0.14.1 | Identification of data source
0.14.2 | Selection of personnel
0.15 | Required Libraries
0.15.1 | Selection of needed libraries
0.16 | Dataset Visualization
0.16.1 | Choosing visualization tool
0.16.2 | Select features for visualization: data types, spread
0.17 | Data Integrity checks
0.17.1 | Review Shape of Distribution
0.17.2 | Check for Missing Values
0.17.3 | Check for data imbalance
0.17.4 | Check for Outliers
0.17.5 | Examine category labels
0.17.6 | Check for scale of magnitude
0.17.7 | Variable ineffectiveness
0.17.8 | Variable correlation
0.18 | Right Fit Model Selection
0.18.1 | Examine business question
0.18.2 | Understand difference between algorithms
0.18.3 | Selection of right model
0.19 | Training Model
0.19.1 | Selection of data to train on
0.19.2
0.2 | Testing Model
0.20.1 | Selection of test size
0.20.2 | Selection of model parameters
0.21 | Evaluated Model
0.21.1 | Understand difference between KPIs
0.21.2 | Selection of right KPI
0.21.3 | Assessment of model
0.22 | Refined Model
0.22.1 | Comparision of model runs
0.22.2 | Selection of model
0.23 | Deployed Model
0.23.1 | Selection of platform
0.24 | Results Reporting
0.24.1 | Selection of Audience
0.24.2 | Selection of presentation
0.25 | Model Monitor & Review
0.25.1 | Change test set size
0.25.2 | Change input parameters

## Sequence Proj Activity
|  | WBS Id | Activity | Predecessor
|  | 0.17 | Data Integrity Checks
0.17 | Data Integrity Checks | 0.17.1 | Review Shape of Distribution | 0.16.1
0.17.1 | Review Shape of Distribution | 0.17.2 | Check for Missing Values | 0.16.1
0.17.2 | Check for Missing Values | 0.17.3 | Check for data imbalance | 0.16.1
0.17.3 | Check for data imbalance | 0.17.4 | Check for Outliers | 0.16.1
0.17.4 | Check for Outliers | 0.17.5 | Examine category labels | 0.16.1
0.17.5 | Examine category labels | 0.17.6 | Check for scale of magnitude | 0.16.1
0.17.6 | Check for scale of magnitude | 0.17.7 | Variable ineffectiveness | 0.16.1
0.17.7 | Variable ineffectiveness | 0.17.8 | Variable correlation | 0.16.1
0.17.8 | Variable correlation
|  | 0.18 | Right Fit Model Selection
0.18 | Right Fit Model Selection | 0.18.1 | Examine business question | 0.11.1, 0.11.2, 0.14.2
0.18.1 | Examine business question | 0.18.2 | Understand difference between algorithms
0.18.2 | Understand difference between algorithms | 0.18.3 | Selection of right model | 0.18.1, 0.18.2
0.18.3 | Selection of right model
0.21 | Evaluated Model | 0.21 | Evaluated Model
0.21.1 | Understand difference between KPIs | 0.21.1 | Understand difference between KPIs
0.21.2 | Selection of right KPI | 0.21.2 | Selection of right KPI | 0.20.1
0.21.3 | Assessment of model | 0.21.3 | Assessment of model | 0.21.1, 0.21.2